## Product Backlog
Gift E-Commerce website
PRODUCT BACKLOG
[13 empty] | MEMBER LOCS CALCULATOR | Nhập MSSV vào ô dưới đây
Function Name | Feature | Complexity | In-charge Roll Number | In-charge Full Name | STATUS | LOCS | Planned confirm | Planned Code Iteration | Actual Code Iteration |  |  |  | 6660 | SE160104
Create Product (Form Validation + Image Upload) | [Staff] Product Management | Medium | SE160104 (FE) SE160104 (BE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Confirm | 120 | Construction 1 | Iteration 1 | Iteration 1 | SE160104 | DucDMD | Đào Mai Duy Đức | 240 | SE160104
View products (pagination) | [Staff] Product Management | Complex | SE160104 (FE) SE160104 (BE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Confirm | 240 | Construction 1 | Iteration 1 | Iteration 1 | SE160874 | TanN | Nguyễn Tấn | 480 | SE160104
View a Product detail | [Staff] Product Management | Medium | SE160104 (FE) SE160104 (BE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Confirm | 120 | Construction 1 | Iteration 1 | Iteration 1 | SE160862 | QuyetTC | Trần Cương Quyết | 240 | SE160104
Edit Product (Form Validation + Image Upload) | [Staff] Product Management | Medium | SE160104 (FE) SE160104 (BE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Confirm | 120 | Construction 1 | Iteration 1 | Iteration 1 | SE160869 | ThienNH | Nguyễn Hoàng Thiện | 240 | SE160104
Delete Product | [Staff] Product Management | Simple | SE160104 (FE) SE160104 (BE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Confirm | 60 | Construction 1 | Iteration 1 | Iteration 1 | SE160848 | LocDT | Đặng Thiêm Lộc | 120 | SE160104
Search Products (pagination) | [Staff] Product Management | Simple | SE160104 (FE) SE160104 (BE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Confirm | 60 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 120 | SE160104
Filter Products by category | [Staff] Product Management | Simple | SE160104 (FE) SE160104 (BE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Confirm | 60 | Construction 1 | Iteration 2 | Iteration 1 |  |  |  | 120 | SE160104
View sorted products by name/price/sold/rating | [Staff] Product Management | Medium | SE160104 (FE) SE160104 (BE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Confirm | 120 | Construction 1 | Iteration 2 | Iteration 1 |  |  |  | 240 | SE160104
Login by username & password | Login | Simple | SE160104 (FE) SE160104 (BE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Confirm | 60 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 120 | SE160104
Logout | Logout | Simple | SE160104 (FE) | Đào Mai Duy Đức | Confirm | 60 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 60 | SE160104
Register for guest to customer | Register | Simple | SE160104 (FE) SE160104 (BE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Done | 60 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 120 | SE160104
Reset password | [User] Reset password | Complex | SE160104 (FE) SE160862 (BE) SE160874 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) Nguyễn Tấn (BE) | Done | 240 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 240 | SE160104
View products in shop (pagination) | [Guest] Shopping | Complex | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Done | 240 | Construction 2 | Iteration 1 | Iteration 1 |  |  |  | 240 | SE160104
Search Products (pagination) | [Guest] Shopping | Simple | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Done | 60 | Construction 2 | Iteration 1 | Iteration 1 |  |  |  | 60 | SE160104
View a Product detail | [Guest] Shopping | Simple | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Done | 60 | Construction 2 | Iteration 1 | Iteration 1 |  |  |  | 60 | SE160104
Suggest similar products | [Guest] Shopping | Simple | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Done | 60 | Construction 2 | Iteration 1 | Iteration 1 |  |  |  | 60 | SE160104
Filter Products by category | [Guest] Shopping | Simple | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Done | 60 | Construction 2 | Iteration 1 | Iteration 1 |  |  |  | 60 | SE160104
View sorted products by name/price/sold/rating | [Guest] Shopping | Medium | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Done | 120 | Construction 2 | Iteration 1 | Iteration 1 |  |  |  | 120 | SE160104
View reviews/feedbacks for each product | [Guest] Shopping | Simple | SE160104 (FE) SE160869 (BE) | Đào Mai Duy Đức (FE) Nguyễn Hoàng Thiện (BE) | Done | 60 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 60 | SE160104
View products in shop (pagination) | [Customer] Shopping | Complex | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Confirm | 240 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 240 | SE160104
Search Products (pagination) | [Customer] Shopping | Simple | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Confirm | 60 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 60 | SE160104
View a Product detail | [Customer] Shopping | Simple | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Confirm | 60 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 60 | SE160104
Suggest similar products | [Customer] Shopping | Simple | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Confirm | 60 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 60 | SE160104
Filter Products by category | [Customer] Shopping | Simple | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Confirm | 60 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 60 | SE160104
View sorted products by name/price/sold/rating | [Customer] Shopping | Medium | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Confirm | 120 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 120 | SE160104
Buy now | [Customer] Shopping | Medium | SE160104 (FE) SE160869 (BE) | Đào Mai Duy Đức (FE) Nguyễn Hoàng Thiện (BE) | Done | 120 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 120 | SE160104
View reviews/feedbacks for each product | [Customer] Shopping | Simple | SE160104 (FE) SE160869 (BE) | Đào Mai Duy Đức (FE) Nguyễn Hoàng Thiện (BE) | Done | 60 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 60 | SE160104
View customer profile | [Customer] View profile | Simple | SE160848 (FE) SE160874 (BE) | Đặng Thiêm Lộc (FE) Nguyễn Tấn (BE) | Done | 60 | Construction 2 | Iteration 2 | Iteration 2 |  |  |  | 0 | SE160104
Edit customer profile | [Customer] Edit profile | Simple | SE160848 (FE) SE160862 (BE) | Đặng Thiêm Lộc (FE) Trần Cương Quyết (BE) | Done | 60 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 0 | SE160104
View staff profile | [Staff] View account profile | Simple | SE160848 (FE) SE160874 (BE) | Đặng Thiêm Lộc (FE) Nguyễn Tấn (BE) | Done | 60 | Construction 2 | Iteration 2 | Iteration 2 |  |  |  | 0 | SE160104
View manager profile | [Manager] View account profile | Simple | SE160848 (FE) SE160874 (BE) | Đặng Thiêm Lộc (FE) Nguyễn Tấn (BE) | Done | 60 | Construction 2 | Iteration 2 | Iteration 2 |  |  |  | 0 | SE160104
Edit manager profile | [Manager] Edit account profile | Simple | SE160848 (FE) SE160862 (BE) | Đặng Thiêm Lộc (FE) Trần Cương Quyết (BE) | Done | 60 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 0 | SE160104
Add products to cart (Cart.refresh() => sync database) | [Customer] Shopping Cart actions | Complex | SE160104 (FE) SE160869 (BE) | Đào Mai Duy Đức (FE) Nguyễn Hoàng Thiện (BE) | Done | 240 | Construction 2 | Iteration 2 | Iteration 2 |  |  |  | 240 | SE160104
View products in cart (with pagination) (Cart.refreshAll() => => sync database) | [Customer] Shopping Cart actions | Complex | SE160104 (FE) SE160874 (BE) | Đào Mai Duy Đức (FE) Nguyễn Tấn (BE) | Done | 240 | Construction 2 | Iteration 2 | Iteration 2 |  |  |  | 240 | SE160104
Delete product in cart | [Customer] Shopping Cart actions | Simple | SE160104 (FE) SE160874 (BE) | Đào Mai Duy Đức (FE) Nguyễn Tấn (BE) | Done | 60 | Construction 2 | Iteration 2 | Iteration 2 |  |  |  | 60 | SE160104
Edit information of product in cart (Cart.refresh() => => sync database) | [Customer] Shopping Cart actions | Complex | SE160104 (FE) SE160869 (BE) | Đào Mai Duy Đức (FE) Nguyễn Hoàng Thiện (BE) | Done | 240 | Construction 2 | Iteration 2 | Iteration 2 |  |  |  | 240 | SE160104
Checkout (select -> forms -> order) | [Customer] Checkout | Complex | SE160104 (FE) SE160874 (BE) | Đào Mai Duy Đức (FE) Nguyễn Tấn (BE) | Done | 240 | Construction 2 | Iteration 2 | Iteration 2 |  |  |  | 240 | SE160104
Add payment service (Paypal) | Order Payment Method | Medium | SE160104 (FE) SE160104 (FE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Done | 120 | Construction 2 | Iteration 3 | Iteration 2 |  |  |  | 120 | SE160104
Add shipping service (giaohangnhanh) | Orders Delivery Management | Medium | SE160104 (FE) SE160104 (FE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Done | 120 | Construction 3 | Iteration 3 | Iteration 2 |  |  |  | 120 | SE160104
View orders placed (with pagination) | [Customer] Order Management | Complex | SE160104 (FE) SE160874 (BE) | Đào Mai Duy Đức (FE) Nguyễn Tấn (BE) | Done | 240 | Construction 2 | Iteration 2 |  |  |  |  | 240 | SE160104
View orders placed followed status | [Customer] Order Management | Simple | SE160104 (FE) SE160104 (FE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Done | 60 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 60 | SE160104
View detail of each order | [Customer] Order Management | Medium | SE160104 (FE) SE160869 (BE) | Đào Mai Duy Đức (FE) Nguyễn Hoàng Thiện (BE) | Done | 120 | Construction 2 | Iteration 2 |  |  |  |  | 120 | SE160104
Cancel pending order | [Customer] Order Management | Simple | SE160104 (FE) SE160869 (BE) | Đào Mai Duy Đức (FE) Nguyễn Hoàng Thiện (BE) | Done | 60 | Construction 3 | Iteration 2 |  |  |  |  | 60 | SE160104
Buy again based on order | [Customer] Order Management | Simple | SE160104 (FE) SE160104 (FE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Done | 60 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 60 | SE160104
Rating/Feedback for successful orders | [Customer] Order Management | Complex | SE160104 (FE) SE160874 (BE) | Đào Mai Duy Đức (FE) Nguyễn Tấn (BE) | Done | 240 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 240 | SE160104
View orders placed by customers (with pagination) | [Staff] Order Management | Complex | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Done | 240 | Construction 3 | Iteration 2 | Iteration 3 |  |  |  | 240 | SE160104
View orders by status | [Staff] Order Management | Simple | SE160104 (FE) SE160104 (FE) | Đào Mai Duy Đức (FE) Đào Mai Duy Đức (BE) | Done | 60 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 60 | SE160104
View detail of each order | [Staff] Order Management | Medium | SE160104 (FE) SE160874 (BE) | Đào Mai Duy Đức (FE) Nguyễn Tấn (BE) | Done | 120 | Construction 3 | Iteration 2 | Iteration 3 |  |  |  | 120 | SE160104
Refuse/Confirm orders (include email sending to customer) | [Staff] Order Management | Medium | SE160104 (FE) SE160862 (BE) | Đào Mai Duy Đức (FE) Trần Cương Quyết (BE) | Done | 120 | Construction 3 | Iteration 2 | Iteration 3 |  |  |  | 120 | SE160104
Update Order State | [Staff] Order Management | Simple | SE160104 (FE) SE160874 (BE) | Đào Mai Duy Đức (FE) Nguyễn Tấn (BE) | Done | 60 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 60 | SE160104
View staff list | [Manager] Staff management | Medium | SE160848 (FE) SE160869 (BE) | Đặng Thiêm Lộc (FE) Nguyễn Hoàng Thiện (BE) | Confirm | 120 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 0 | SE160104
Search staffs by name, username or email | [Manager] Staff management | Medium | SE160848 (FE) SE160869 (BE) | Đặng Thiêm Lộc (FE) Nguyễn Hoàng Thiện (BE) | Confirm | 120 | Construction 1 | Iteration 1 | Iteration 1 |  |  |  | 0 | SE160104
View detail staff profile | [Manager] Staff management | Simple | SE160848 (FE) SE160869 (BE) | Đặng Thiêm Lộc (FE) Nguyễn Hoàng Thiện (BE) | Done | 60 | Construction 2 | Iteration 1 | Iteration 1 |  |  |  | 0 | SE160104
Add new staff | [Manager] Staff management | Simple | SE160848 (FE) SE160869 (BE) | Đặng Thiêm Lộc (FE) Nguyễn Hoàng Thiện (BE) | Done | 60 | Construction 3 | Iteration 2 | Iteration 1 |  |  |  | 0 | SE160104
Edit already staff profile | [Manager] Staff management | Simple | SE160848 (FE) SE160869 (BE) | Đặng Thiêm Lộc (FE) Nguyễn Hoàng Thiện (BE) | Done | 60 | Construction 3 | Iteration 2 | Iteration 1 |  |  |  | 0 | SE160104
Delete staff | [Manager] Staff management | Simple | SE160848 (FE) SE160869 (BE) | Đặng Thiêm Lộc (FE) Nguyễn Hoàng Thiện (BE) | Done | 60 | Construction 2 | Iteration 2 | Iteration 1 |  |  |  | 0 | SE160104
Overview statistics | [Manager] Revenue statistics | Medium | SE160104 (FE) SE160874 (BE) | Đào Mai Duy Đức (FE) Nguyễn Tấn (BE) | Done | 120 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 120 | SE160104
Revenue statistics | [Manager] Revenue statistics | Medium | SE160104 (FE) SE160869 (BE) | Đào Mai Duy Đức (FE) Nguyễn Hoàng Thiện (BE) | Done | 120 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 120 | SE160104
Order statistics | [Manager] Order statistics | Medium | SE160104 (FE) SE160874 (BE) | Đào Mai Duy Đức (FE) Nguyễn Tấn (BE) | Done | 120 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 120 | SE160104
Product statistics | [Manager] Product statistics | Medium | SE160104 (FE) SE160869 (BE) | Đào Mai Duy Đức (FE) Nguyễn Hoàng Thiện (BE) | Done | 120 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 120 | SE160104
Customer statistics | [Manager] Customer statistics | Medium | SE160104 (FE) SE160874 (BE) | Đào Mai Duy Đức (FE) Nguyễn Tấn (BE) | Done | 120 | Construction 3 | Iteration 3 | Iteration 3 |  |  |  | 120 | SE160104
[13 empty] | 6660 | SE160104