## W1
PROJECT REPORT
Group | Codies
Week | <08/05/2023-13/05/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Teamwork Setup | Completed | Meetings, and consistent how team collaboration that including like members, roles, work, time, management...
2 | Product Backlog | In Progress | List functions, features.
3 | SRS | In Progress | Overall contents as listed in the part I of the SRS document.
4 | Design document | In Progress | Overall contents as listed in the part I of the Design Document.
5 | UI/UX design | In Progress | Design basic layouts and components for screens order by priority followed the product backlog.
6 | Code Project Initialization | In Progress | Initialize the first code (Spring) for the project & set up source code control.
7 | Weekly Report | Completed | Summarize and complete the work report for the week.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Teamwork Setup | DucDMD | Lead & host meetings, and consistent how team collaboration & resource management.
2 | Product Backlog | DucDMD | List functions, features.
3 | SRS | TanN, QuyetTC, ThienNH, LocDT | Complete the basic requirements overview & related partial diagrams as listed in part I of the SRS document.
4 | Design document | DucDMD, TanN, ThienNH, QuyetTC | Complete basic code package diagram & description as listed in the part I of the Design Document.
5 | UI/UX design | QuyetTC, DucDMD, TanN, LocDT | Design basic wireframe layouts and components for some basic screens by "Mockplus".
6 | Code Project Initialization | DucDMD | Initialize the first code (Spring) for the project & the first commits to VCS (Github).
7 | Weekly Report | DucDMD | Summarize and complete the work report for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | UI/UX design | Completed | The team lacks experience with UI design tools, the solution is to learn by doing parallelly while working toward the week-mentioned objectives.
2 | Frontend skill requirements | In Progress | Team FE lacks some knowledge about working with REST API, so the team offers training parallelly solutions before entering the construction phase.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Product Backlog | 2023-05-16 | Continue to refine and complete the product backlog.
2 | SRS | 2023-05-18 | Continue to refine and complete the SRS document.
3 | SDD | 2023-05-18 | Continue to refine and complete the the Design Document.
4 | UI/UX design | 2023-05-18 | Complete basic UI/UX for the first basic screens (priority followed backlog).
5 | Database Schema Design | 2023-05-18 | Complete basic database schema design meets business logic & data domain to the app.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W2
PROJECT REPORT
Group | Codies
Week | <15/05/2023-20/05/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Product Backlog | Completed | List functions, features.
2 | SRS | Completed | Overall contents as listed in the part I of the SRS document.
3 | Design document | Completed | Overall contents as listed in the part I of the Design Document.
4 | UI/UX design | In Progress | Design basic layouts and components for screens order by priority followed the product backlog.
5 | Code Project Initialization | Completed | Initialize the first code (Spring) for the project & set up source code control.
6 | Database Schema Design | Completed | Complete basic database schema design meets business logic & data domain to the app
7 | Weekly Report | Completed | Summarize and complete the work report for the week.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Product Backlog | DucDMD | List functions, features.
2 | SRS | TanN, QuyetTC, ThienNH, LocDT | Complete the basic requirements overview & related diagrams as listed in part I of the SRS document.
3 | Design document | DucDMD, TanN, ThienNH, QuyetTC | Complete basically the part I of the Design Document.
4 | UI/UX design | QuyetTC, DucDMD, TanN, LocDT | Design basic wireframe layouts and components for some first basic screens by "Mockplus".
5 | Code Project Initialization | DucDMD | Continue set up (Spring) for the project & commit to VCS (Github).
6 | Database Schema Design | DucDMD, TanN | Complete the first basic database schema design meets business logic & data domain to the app.
7 | Weekly Report | DucDMD | Summarize and complete the work report for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Frontend skill requirements | In Progress | Team FE lacks some knowledge about working with REST API, so the team offers training parallelly solutions before entering the construction phase.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Product Backlog | 2023-05-22 | Continue to refine and complete the product backlog for complexity, planned code iteration, dividing tasks.
2 | SRS | Update week by week | Continue to refine and complete the SRS document.
3 | SDD | Update week by week | Continue to refine and complete the part II of the Design Document.
4 | Backend Code Project Setup | 2023-05-25 | Complete basic setup environment, configuration, and structure for the project including connecting with DBMS (mySQL).
5 | API Endpoints Design | 2023-05-25 | Design big pictures API endpoints for the project, and some specific API endpoints for first implementation features.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W3
PROJECT REPORT
Group | Codies
Week | <22/05/2023-27/05/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Product Backlog | Completed | Refine features list, divide & assign tasks for members.
2 | SRS | In Progress | Continue to refine and complete the part II of the SRS document.
3 | Design document | In Progress | Continue to refine and complete the part II of the Design Document.
4 | Frontend & Backend Code Project Setup | Completed | Initialize the first code (Spring & React) for the project & set up source code control.
5 | Backend APIs building | In Progress | Complete basic APIs followed the priority in the backlog.
6 | Frontend UI building | In Progress | Complete basic UI/UX followed the priority in the backlog.
7 | Complete the features followed the backlog | In Progress | Complete basic the features followed backlog by collaborating between FE & BE.
8 | Weekly Report | Completed | Summarize and complete the work report for the week.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Product Backlog | DucDMD | Refine features list, divide & assign tasks for members.
2 | SRS | QuyetTC, TanN, ThienNH, LocDT | Continue to refine and complete the part II of the SRS document.
3 | Design document | TanN, ThienNH, QuyetTC, LocDT | Continue to refine and complete the part II of the Design Document.
4 | Frontend & Backend Code Project Setup | DucDMD | Initialize the first code (Spring & React) for the project & set up source code control.
5 | Backend APIs building | DucDMD, QuyetTC, ThienNH, TanN | Complete basic APIs followed the priority in the backlog.
6 | Frontend UI building | DucDMD, LocDT | Complete basic UI/UX followed the priority in the backlog.
7 | Complete the features followed the backlog | DucDMD, QuyetTC, LocDT, ThienNH | Complete basic the features followed backlog by collaborating between FE & BE.
8 | Weekly Report | DucDMD | Summarize and complete the work report for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | FE team has a little shortage of human resources and experience compared to requirements about the quantity and quality of the project's work. | In Progress | DucDMD has been training knowledge and skills in the real project for LocDT
2 | Some team members still have difficulties with business logic. | In Progress | Improving app business logic understanding parallelly with coding each feature.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Backend APIs building | Update day by day | Complete basic APIs followed the priority in the backlog.
2 | Frontend UI building | Update day by day | Complete basic UI/UX followed the priority in the backlog.
3 | Complete the features followed the backlog | Update day by day | Complete basic the features followed backlog by collaborating between FE & BE.
4 | SRS | Update week by week | Continue to update and refine SRS.
5 | Design document | Update week by week | Continue to update and refine Design document.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W4
PROJECT REPORT
Group | Codies
Week | <29/05/2023-03/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Product Backlog | Completed | Refine features list, divide & assign tasks for members.
2 | SRS | In Progress | Continue to refine and complete the part II of the SRS document.
3 | Design document | In Progress | Continue to refine and complete the part II of the Design Document.
4 | Backend APIs building | Completed | Complete basic APIs followed the priority in the backlog.
5 | Frontend UI building | Completed | Complete basic UI/UX followed the priority in the backlog.
6 | Complete the features followed the backlog | Completed | Complete basic the features followed backlog by collaborating between FE & BE.
7 | Weekly Report | Completed | Summarize and complete the work report for the week.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Product Backlog | DucDMD | Refine features list, divide & assign tasks for members.
2 | SRS | QuyetTC, TanN, ThienNH, LocDT | Continue to refine and complete the part II of the SRS document.
3 | Design document | TanN, ThienNH, QuyetTC, LocDT | Continue to refine and complete the part II of the Design Document.
4 | Backend APIs building | DucDMD, QuyetTC, ThienNH, TanN | Complete basic APIs followed the priority in the backlog.
5 | Frontend UI building | DucDMD, LocDT | Complete basic UI/UX followed the priority in the backlog.
6 | Complete the features followed the backlog | DucDMD, QuyetTC, LocDT, ThienNH | Complete basic the features followed backlog by collaborating between FE & BE.
7 | Weekly Report | DucDMD | Summarize and complete the work report for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | FE team has a little shortage of human resources and experience compared to requirements about the quantity and quality of the project's work. | In Progress | DucDMD has been training knowledge and skills directly in the project for LocDT
2 | Some team members still have difficulties with business logic. | In Progress | Improving app business logic understanding parallelly with coding each feature.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Backend APIs building | Update day by day | Complete basic APIs followed the priority in the backlog.
2 | Frontend UI building | Update day by day | Complete basic UI/UX followed the priority in the backlog.
3 | Complete the features followed the backlog | Update day by day | Complete basic the features followed backlog by collaborating between FE & BE.
4 | SRS | Update week by week | Continue to update and refine SRS.
5 | Design document | Update week by week | Continue to update and refine Design document.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W5
PROJECT REPORT
Group | Codies
Week | <05/06/2023-10/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Product Backlog | Completed | Refine features list, divide & assign tasks for members.
2 | SRS | In Progress | Continue to refine and complete the part II of the SRS document.
3 | Design document | In Progress | Continue to refine and complete the part II of the Design Document.
4 | Backend APIs building | In Progress | Complete basic APIs followed the priority in the backlog.
5 | Frontend UI building | In Progress | Complete basic UI/UX followed the priority in the backlog.
6 | Complete the features followed the backlog | In Progress | Complete basic the features followed backlog by collaborating between FE & BE.
7 | Weekly Report | Completed | Summarize and complete the work report for the week.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Product Backlog | DucDMD | Refine features list, divide & assign tasks for members.
2 | SRS | QuyetTC, TanN, ThienNH, LocDT | Continue to refine and complete the part II of the SRS document.
3 | Design document | TanN, ThienNH, QuyetTC, LocDT | Continue to refine and complete the part II of the Design Document.
4 | Backend APIs building | DucDMD, QuyetTC, ThienNH, TanN | Complete basic APIs followed the priority in the backlog.
5 | Frontend UI building | DucDMD, LocDT | Complete basic UI/UX followed the priority in the backlog.
6 | Complete the features followed the backlog | DucDMD, QuyetTC, LocDT, ThienNH | Complete basic the features followed backlog by collaborating between FE & BE.
7 | Weekly Report | DucDMD | Summarize and complete the work report for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | FE team has a little shortage of human resources and experience compared to requirements about the quantity and quality of the project's work. | Completed | DucDMD has been training knowledge and skills directly in the project for LocDT
2 | Some team members still have difficulties with business logic. | Completed | Improving app business logic understanding parallelly with coding each feature.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Backend APIs building | Update day by day | Complete basic APIs followed the priority in the backlog.
2 | Frontend UI building | Update day by day | Complete basic UI/UX followed the priority in the backlog.
3 | Complete the features followed the backlog | Update day by day | Complete basic the features followed backlog by collaborating between FE & BE.
4 | SRS | Update week by week | Continue to update and refine SRS.
5 | Design document | Update week by week | Continue to update and refine Design document.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W6
PROJECT REPORT
Group | Codies
Week | <12/06/2023-17/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Product Backlog | Completed | Refine features list, divide & assign tasks for members.
2 | SRS | Completed | Continue to refine and complete the part II of the SRS document.
3 | Design document | Completed | Continue to refine and complete the part II of the Design Document.
4 | Backend APIs building | Completed | Complete basic APIs followed the priority in the backlog.
5 | Frontend UI building | Completed | Complete basic UI/UX followed the priority in the backlog.
6 | Complete the features followed the backlog | Completed | Complete the features followed backlog by collaborating between FE & BE.
7 | Weekly Report | Completed | Summarize and complete the work report for the week.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Product Backlog | DucDMD | Refine features list, divide & assign tasks for members.
2 | SRS | QuyetTC, TanN, ThienNH, LocDT | Continue to refine and complete the part II of the SRS document.
3 | Design document | TanN, ThienNH, QuyetTC, LocDT | Continue to refine and complete the part II of the Design Document.
4 | Backend APIs building | DucDMD, QuyetTC, ThienNH, TanN | Complete basic APIs followed the priority in the backlog.
5 | Frontend UI building | DucDMD, LocDT | Complete basic UI/UX followed the priority in the backlog.
6 | Complete the features followed the backlog | DucDMD, QuyetTC, LocDT, ThienNH | Complete the features followed backlog by collaborating between FE & BE.
7 | Weekly Report | DucDMD | Summarize and complete the work report for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Backend APIs building | Update day by day | Complete basic APIs followed the priority in the backlog.
2 | Frontend UI building | Update day by day | Complete basic UI/UX followed the priority in the backlog.
3 | Complete the features followed the backlog | Update day by day | Complete the features followed backlog by collaborating between FE & BE.
4 | SRS | Update week by week | Continue to update and refine SRS.
5 | Design document | Update week by week | Continue to update and refine Design document.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W7
PROJECT REPORT
Group | Codies
Week | <19/06/2023-24/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Product Backlog | Completed | Refine features list, divide & assign tasks for members.
2 | SRS | In Progress | Continue to refine and complete the part II of the SRS document.
3 | Design document | In Progress | Continue to refine and complete the part II of the Design Document.
4 | Backend APIs building | In Progress | Complete basic APIs followed the priority in the backlog.
5 | Frontend UI building | In Progress | Complete basic UI/UX followed the priority in the backlog.
6 | Complete the features followed the backlog | In Progress | Complete the features followed backlog by collaborating between FE & BE.
7 | Weekly Report | Completed | Summarize and complete the work report for the week.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Product Backlog | DucDMD | Refine features list, divide & assign tasks for members.
2 | SRS | QuyetTC, TanN, ThienNH, DucDMD, LocDT | Continue to refine and complete the part II of the SRS document.
3 | Design document | TanN, ThienNH, QuyetTC, DucDMD, LocDT | Continue to refine and complete the part II of the Design Document.
4 | Backend APIs building | DucDMD, QuyetTC, ThienNH, TanN | Complete basic APIs followed the priority in the backlog.
5 | Frontend UI building | DucDMD, LocDT | Complete basic UI/UX followed the priority in the backlog.
6 | Complete the features followed the backlog | DucDMD, TanN, QuyetTC, LocDT, ThienNH | Complete the features followed backlog by collaborating between FE & BE.
7 | Weekly Report | DucDMD | Summarize and complete the work report for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Backend APIs building | Update day by day | Complete basic APIs followed the priority in the backlog.
2 | Frontend UI building | Update day by day | Complete basic UI/UX followed the priority in the backlog.
3 | Complete the features followed the backlog | Update day by day | Complete the features followed backlog by collaborating between FE & BE.
4 | SRS | Update week by week | Continue to update and refine SRS.
5 | Design document | Update week by week | Continue to update and refine Design document.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W8
PROJECT REPORT
Group | Codies
Week | <26/06/2023-28/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Product Backlog | Completed | Refine features list, divide & assign tasks for members.
2 | SRS | Completed | Complete the SRS document.
3 | Design document | Completed | Complete the Design Document.
4 | Backend APIs building | Completed | Complete basic APIs followed the priority in the backlog.
5 | Frontend UI building | Completed | Complete basic UI/UX followed the priority in the backlog.
6 | Complete the features followed the backlog | Completed | Complete the features followed backlog by collaborating between FE & BE.
7 | Testing & refine comprehensive for the final outcome (webapp). | In Progress | Testing & refine comprehensive for the final outcome (webapp).
8 | Weekly Report | Completed | Summarize and complete the work report for the week.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Product Backlog | DucDMD | Refine features list, divide & assign tasks for members.
2 | SRS | QuyetTC, TanN, ThienNH, DucDMD, LocDT | Complete the SRS document.
3 | Design document | TanN, ThienNH, QuyetTC, DucDMD, LocDT | Complete the Design Document.
4 | Backend APIs building | DucDMD, QuyetTC, ThienNH, TanN | Complete basic APIs followed the priority in the backlog.
5 | Frontend UI building | DucDMD, LocDT | Complete basic UI/UX followed the priority in the backlog.
6 | Complete the features followed the backlog | DucDMD, TanN, QuyetTC, LocDT, ThienNH | Complete the features followed backlog by collaborating between FE & BE.
7 | Testing & refine comprehensive for the final outcome (webapp). | DucDMD, QuyetTC, LocDT | Testing & refine comprehensive for the final outcome (webapp).
7 | Weekly Report | DucDMD | Summarize and complete the work report for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Testing & refine comprehensive for the final outcome (webapp). | 2023-07-01 | Testing & refine comprehensive for the final outcome (webapp).
2 | Final Presentation Preparation | 2023-07-08 | Final Presentation Preparation
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## Wx
PROJECT REPORT
Group | Codies
Week | <dd/mm/yyyy-dd/mm/yyyy>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes